## Task
Task ID | Issue ID | Phase | Category | Type | Task / Element | Priority | Responsible | Status | Planned Start Date | Actual Start Date | Next Checkpoint | Planned End Date | Actual End Date | Resolution | Comment | Feedback from Meeting (Oct 12) | Focus for the Meeting (Oct 19) | Feedback from Meeting (Oct 21)
1 |  | 1 | IT infrastructure | Clarification | Connection from R to local MariaDB worked. It worked with MariaDB server based once so we have ruled out that it is the access/connection issue. Can we add exception so that R can connect to MariaDB? | High | Alban | Completed |  | 2016-10-12 |  | 2016-10-28 |  | Potentially, MySQL configuration is missing in the server | Can connect to MariaDB using R via local computer |  |  | Alban will look into it.
2 |  | 1 | IT infrastructure | Request | Full access to MySQL server (backup if RMySQL still cannot connect to DB engine) | High | Alban | Completed |  | 2016-10-12 |  | 2016-10-28 |  |  | Ability to create CSV files on the server | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19 |  | Alban will look into it.
3 |  | 1 | IT infrastructure | Request | Additional user account for Adrian (MAC user) | High | Giao | Overdue | 2016-10-21 | 2016-10-21 |  | 2016-11-21 |  | Email has been sent to Giao | VPN, SSH, MySQL; including RW access to the shared folder. Jan sent email to Giao on week Oct 24 to | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19 |  | Jan will reach out to Jao to create the user
4 |  | 1 | Project Management | Request | Point person / project manager for this project from Etancesys | High |  | Overdue | 2016-10-21 |  |  | 2016-11-21
5 |  | 1 | Data | Clarification | What's are the differences among the duplicate columns per category in AQO? | High | Alban | Completed |  | 2021-10-01 |  |  |  |  | Is the qoe_rules the right table? |  |  | The duplicate variables are stored in different tables, the calcualtion are the same but aggregated differently. Alban will send the table that has the calculation. The aggregation are based on the Axis of Analysis table
6 |  | 1 | Data | Clarification | Why are some of the variables still not renamed based on the new naming convention from the Objects Query Mapping | High | Karim / Alban | Completed |  | 2021-10-01 |  |  |  |  | Still waiting for the data definition for each column |  |  | Alban will check it. Jovan will send an email to followup. In Tunisia, they're using 1.1 and soon will use 1.2 soon. Ignore 1.5. In 1.2 theres a table that contains all the definition, also that the names are changed. If Mali decides to migrate to cloud, they will migrate to 1.2 in a month or so. Karim will build a small sample based on Tunisia. Alban will build either 1M of subscribers for 2 weeks of data or 4M of scubscribers for 1 week. Sometime midnext week, he will provide sample data with all details.
7 |  | 1 | IT infrastructure | Clarification | How to handle software requirements, i.e.: PERL, exploratory.io | High | Rowen | Overdue | 2016-10-21 | 2016-10-21 |  | 2016-11-04 |  |  | Rowen will test perl and will look for alternative ETL that runs under perl |  |  | Python could still be there, Karim's team uses Java and C. Peritus will look into exploratory package we can use based on those languages. ETL will still have to stay low-level. No perl
8 |  | 1 | Documentation | Request | Look up tables - subscriber information documentation | Low |  | Completed |  | 2012-10-01 | [5 empty] | Not available
9 |  | 1 | Documentation | Request | Look up tables - cellsite information documentation | Low |  | Completed |  | 2012-10-01 | [5 empty] | Not available
10 |  | 1 | Documentation | Request | Look up tables - geographic documentation | Low |  | Completed |  | 2012-10-01 | [5 empty] | Not available
11 |  | 1 | Documentation | Request | Look up tables - handset database documentation | Low |  | Completed |  | 2012-10-01 | [5 empty] | Not available
12 |  | 1 | IT infrastructure | Clarification | Shall we improve the current security approach? | Low |  | Completed | [6 empty] | e.g. VNC
13 |  | 1 | IT infrastructure | Clarification | How to change passwords? | Low |  | Completed | [5 empty] | Can only change SSH password | VPN, SSH, MySQL | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19
14 |  | 1 | Data | Request | Look up tables - subscriber information, recent data | Medium | Adrian | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  | Subscriber | File is created daily but not uploaded regularly
15 |  | 1 | Data | Request | Look up tables - cellsite information, recent data | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  | geographical mapping, manufacturer, type | Refer to OSIRIS_PARAMS | Done
16 |  | 1 | Data | Request | Look up tables - geographic, recent data | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  | Marketing zone | Possible but complex approach, estimations of zone are available but not the labeling
17 |  | 1 | Data | Clarification | Why are only 54% of the records populated with IMEI in the subscriber table? | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  |  | Handset info is collected from customer care. On next release, Karim is planning to capture the handset info from the probe
18 |  | 1 | Data | Request | Look up tables - handset database | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  |  | Not available
19 |  | 1 | Data | Clarification | Is it possible to map additional handset information, ie such as supported technology, model category, etc. | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  |  | No
20 |  | 1 | Documentation | Request | Data defintion OTARIE | Medium |  | Completed |  | 2012-10-01 |  | 2012-10-01 |  |  |  | There's not much documentation but most of the columns are self-explanatory
21 |  | 1 | Data | Request | Does the event level data contain the full population of subscriber or just a sample of 2M? Complete event level data for 2 weeks for all products. | Medium | Adrian | Completed | 2016-10-26 | 2016-10-26 |  |  | 2016-12-23 | Etancesys will provide new set of data | Just loaded the imsi table. Will need to join tables to validate active subscriber based on the event level tables | Peritus to backup data to the test database | Currently in progress of backing up data to make a static sample dataset
22 |  | 1 | Documentation | Request | Documentation of QOE hierarchy from Sofrecom | Medium |  | Completed |  |  |  | 2018-10-01
23 |  | 1 | Data | Clarification | How is event level data for data events retained? | Medium |  | Completed | [5 empty] | OTARIE event level is stored in calls_details and calls_details3g | OTARIE | Mustafa will send OTARIE sample data | Jovan will send email to followup with Karim | encode_histo_cols_agreg_***. The lowest level is already this table. If the KPI is 0, it wont be in the table anymore. The rows are aggregated by the hour. The last CI of the call is recorded. He will call Mustafa to verify. Peritus will reach out to Mustapha
24 |  | 1 | Data | Request | KPI level data for the same period as event level data | Medium |  | Completed | [5 empty] | Oct 11 to 18 | Dependency on #57 - Extract blob | Will be clarified later | Followup call today where are the tables?
25 |  | 1 | Data | Request | QOE level data for the same period | Medium |  | Completed | [5 empty] | Oct 11 to 18 |  |  | Followup call today where are the tables?
26 |  | 1 | Data | Request | SQL script for KPIs and QOE | Medium | Alban | Completed |  | 2021-10-01 |  | 2024-10-01 |  | tun.qoe_rules table was created which contains the rules for QOE. KPIs are not available because the calculation are done externally | Export from requestor, possible? Used for indicator classification map dataset | Yes. Alban will provide SQL table and clarifications next week | Received sofrecome data definition but need to verify on the call | Theres an aggregation from the encode_histo_cols_agreg. Theres an additional code that aggregates into a higher KPI calculation into another table. Alban doesn’t know the rules how to create the table. The files from OTARIE are logged into the table without transformation. All KPIs are from mix of OTARIE and CIGALE already.
27 |  | 1 | Documentation | Request | Data defintion CIGALE | High | Karim | Overdue | 2016-10-12 | 2016-10-12 |  |  |  |  | Waiting for v1.2 |  | Received sofrecome data definition but need to verify on the call
28 |  | 1 | Documentation | Request | Clear code documentation of the relevant network elements | Medium | Karim | Overdue | 2016-10-12 | 2016-10-12 |  |  |  |  | Dependency on #68 - ref_cause | Bertrand is the contact person
29 |  | 1 | Documentation | Request | Data definition KPIs | Medium | Karim | Completed |  | 2021-10-01 |  |  |  | Imported directly into cem database without transformation; not derived from CEM events level database
30 |  | 1 | Documentation | Request | Data definition QOE | Medium | Karim | Completed |  | 2021-10-01 |  |  |  | Stored in tun.qoe_rules
31 |  | 1 | IT infrastructure | Clarification | What RAM allocation does the server for the project have? | Low | Alban | Completed | 2012-10-01 | 2012-10-01 |  |  |  | available RAM on R is 60+ GB |  | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19
32 |  | 1 | IT infrastructure | Clarification | What storage capacity does the server for the project have? | Low | Alban | Completed | 2012-10-01 | 2012-10-01 | [5 empty] | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19
33 |  | 1 | IT infrastructure | Clarification | Scheduled downtime? | Low | Alban | Cancelled |  | 2012-10-01 |  |  |  | No downtime occurred in the past few weeks |  | Clarifications will be provided by Alban on next week's meeting on Wed, Oct 19
34 |  | 1 | Project Management | Request | IT contact person | Medium | Karim | Completed |  | 2016-10-12 |  |  |  | Alban and Giao
35 |  | 1 | Project Management | Request | Sofrecom contact person | Medium | Karim | Overdue | 2016-10-12 |  |  | 2016-11-12
36 |  | 1 | Project Management | Request | Probe/osiris expert contact | Medium | Karim | Completed |  | 2016-10-12 |  |  |  |  | Bertrand
37 |  | 1 | Project Management | Request | Regular project meeting schedule | Medium | Karim | Completed |  | 2012-10-01 |  | 41183 |  | Weekly calls for 1st month, afterwards bi-monthly, monthly with Laurent |  | Karim can do bi-monthly meeting the most
38 |  | 1 | Project Management | Clarification | General availability | Medium | Etancesys | Completed |  | 2016-10-12
39 |  | 1 | Project Management | Clarification | Timeline data request (OTARIE) | Medium |  | Cancelled |  | 2012-10-01
40 |  | 1 | Project Management | Clarification | Timeline data documentation request (OTARIE) | Medium |  | Cancelled |  | 2012-10-01
41 |  | 1 | IT infrastructure | Request | Rename test DB to Peritus_Landing | Medium | Alban | Cancelled |  | 2021-10-01 |  | 45566 |  | Created Land instead |  |  |  | Will create 3 databases
42 |  | 1 | IT infrastructure | Request | Create DB: Peritus_Transform and Peritus_Develop | Medium | Alban | Completed |  | 2021-10-01 |  | 45566 |  | Done creating 3 DBs |  |  |  | Will create 3 databases
43 |  | 1 | IT infrastructure | Request | Grant full access rights to tables in Peritus DBs | Medium | Alban | Completed |  | 2016-10-21 |  | 42671 | [5 empty] | Will create 3 databases
44 |  | 1 | Data | Task | Check subscriber table when it is updated | Medium | Adrian | Completed |  | 2016-10-12
45 |  | 1 | Data | Task | Create structure how to handle subscriber history table | Medium | Adrian / Rowen | Cancelled |  | 2016-10-12 |  |  |  | Duplicate of 44
46 |  | 1 | Data | Task | Data collection report - metadata for the tables | Medium | Adrian | Completed |  | 2021-10-01 |  | 45931 |  | Created data inventory and collection report template
47 |  | 1 | Data | Task | Inventory of what we have in the test table | Medium | Rowen | Cancelled |  | 2019-10-01 |  | 46296 |  | Replaced by #58 | Dependent on data inventory and collection report template
48 |  | 1 | Data | Task | Create process flow from table > join > load to R > transform > save R object | Medium | Adrian / Rowen | Completed |  | 2016-10-18 |  | 31/11/2016 |  | Was able to access MariaDB from R. Uses land, dev and trans database | Waiting for access from R to MariaDB
49 |  | 1 | Data | Task | Review translation of data definition | Medium | Jovan | Completed |  | 2016-10-18 |  |  |  | Received 1.2 with French and English descriptions | Waiting for v1.2
50 |  | 1 | Data | Task | Draft the storyboard for the steerico | Medium | Peritus | Completed | 2016-11-02 | 2016-11-02 |  | 2016-11-18 | 2016-11-21
51 |  | 1 | Data | Task | Create project plan for the next 2 weeks | Medium | Adrian | Completed | 2016-10-18 | 2016-11-14 |  | 2016-11-18 |  | Done for steerco 2 | Will discuss on Oct26
52 |  | 1 | Data | Task | Export DB and table overview | Medium | Adrian / Rowen | Cancelled | [5 empty] | Will not use Mali
53 |  | 1 | Data | Clarification | Where in the DS process where the KQI, QOE are calculated? | Medium | Adrian | Completed |  | 2016-10-12 |  | 42669 |  | Data exploration
54 |  | 1 | Project Management | Task | Data collection report template | Medium | Adrian | Completed |  | 2021-10-01 |  | 45566
55 |  | 1 | Data | Clarification | There's no calculation from event level to aggregated on KPI. What's the implication? | Medium | Adrian | Completed |  | 2016-10-25 |  |  |  | Waiting for event data dictionary | Waiting for Bertrand
56 |  | 1 | Data | Task | Request for SQL procedure to extract BLOB | Medium | Adrian | Completed |  | 2016-10-26 |  | 2016-11-04 |  | Expanded tun histo_cols_agreg blob into wide format
57 |  | 1 | Data | Task | Inventory of what we have in the tun and cem_cpt tables | Medium | Rowen | Completed |  | 2025-10-01 |  | 45931 |  | Met with Mustapha on Oct 24 and filled out the description of all the tables from cem_oml, cem_cpt, tun | Dependent on data inventory and collection report template
58 |  | 1 | Data | Clarification | No data yet for calls_details_gprs, reference tables for handset, area, cellsites, lstci and other histo_agreg tables | Medium | Alban | Completed | 2016-10-21 | 2016-10-21 |  |  | 2016-11-11 |  | monthly aggregated tables are not yet populated
59 |  | 1 | Data | Request | Data definition v1.2 | High | Karim | Overdue |  | 2016-10-21 |  |  |  | Received data dictionary for KPI but not for evecnt level yet | Sent 1.2 but only for KPIs
60 |  | 1 | Data | Clarification | Does the event level data contain the full population of subscriber or just a sample of 2M? | Medium | Alban | Cancelled |  | 2016-10-25 |  |  |  | Duplicate of 21
61 |  | 1 | Project Management | Task | Create weekly project status report | Medium | Adrian / Rowen | In Progress | 2016-10-28 | 2016-10-28 |  |  |  |  | In progress
62 |  | 1 | Project Management | Task | Create issue tracker template | Medium | Adrian | Completed |  | 2016-10-26 |  | 2016-10-27 |  | Appended in the Task tab
63 |  |  |  | Task | Identify KPI QOE table in cem_oml a sampler request for tun | Medium | Adrian | Completed |  | 2016-10-26 |  | 42671 |  | KPIs list are different
64 |  |  |  | Task | Verify if ref_cause is also applicable for tun | Medium | Adrian | Completed | 2016-10-26 | 2016-10-26 |  |  |  | Same ref_cause with Mali | Both databases have 50% unused ref_cause. Alban will load the error codes
65 |  |  |  | Clarification | Is OTARIE also included in tun event level data | Medium | Alban | Completed |  | 2016-10-26 |  | 42676
66 |  |  |  | Task | Set meeting with Bertrand | Medium | Jovan | Not Started |  | 2016-10-26 |  |  |  |  | Emailed Karim
67 |  |  |  | Task | Identify lookup fields for data transformation | Medium | Adrian / Jeffrey | Completed | 2016-10-26 | 2016-10-26 |  | 2016-11-09 |  | Reference tables | Looked into reference table that can be used for lookup with the event level tables
68 |  |  |  | Task | Decide on analysis of axis for hierachy reconciliation, request for missing tables | Medium | Jovan | Completed | 2016-10-26 | 2016-10-26 |  | 2016-11-11 |  | Loaded imsi
69 |  |  |  | Task | Draft data quality report | Medium | Jeffry | Completed | 2016-10-26 | 2016-10-26 |  | 2016-11-18 | 2016-11-17 |  | Jeffry sent the structure
70 |  |  |  | Task | Finalize data collection report | Medium | Adrian | Completed |  | 2016-10-26 |  | 2016-11-04 |  | Used information schema on tun database
71 |  |  |  | Task | Look for hierarchy mapping tool | Medium | Jan | Overdue | 2016-10-26 | 2016-10-26 |  |  |  |  | Visio to visualise hierarchy
72 |  |  |  | Task | Sample 1% of calls_details, calls_details3g and calls_details_gprs for exploratory | Medium | Adrian | Completed | 2016-11-04 | 2016-11-04 |  | 2016-11-09 | 2016-11-11 | Done at the event level table | Done with calls_details and calls_details3g.
73 |  |  |  | Task | Populate summary stats on event level tables (calls_details* and histo_cols_agreg*) | Medium | Adrian | Completed | 2016-11-07 | 2016-11-07 |  | 2016-11-15 |  |  | Still not done with weekly summary stat
74 |  |  |  | Issue | Aggregated tables only contain data related KPIs; voice and SMS KPIs have no values | High | Adrian | Completed | 2016-11-07 | 2016-11-07 |  | 2016-11-09 |  | Blob contains all products KPIs
75 |  |  |  | Issue | Incomplete two weeks of event level data | High | Peritus | Completed | 2016-11-16 | [5 empty] | hebdo aggregated tables can only have 1 week of complete data based on the date range of 8-Oct to 18-Oct
76 |  |  |  | Issue | Performance issue when joining tables | Medium | Adrian | Closed | 2016-11-18 |  |  |  | 2016-12-01 | Joining tables will be done in R rather than in SQL. One possible reason is that there are no schemas assigned to the tables.
77 |  |  |  | Task | Top 5000 rows of all tables | Medium | Adrian | Completed | 2016-11-22 | 2016-11-22 |  | 2016-11-22 | 2016-11-22 | Uploaded in OneDrive
78 |  |  |  | Task | Join daily aggregated table with last_mobile and ota_devices | Medium | Adrian | Completed | 2016-11-22 | 2016-11-25 |  | 2016-11-22 | 2016-11-25 | Sent copy to Jeffry
79 |  |  |  | Task | Build QOE-based KPI hierarchy | HIgh | Adrian | Completed | 2016-11-25 | 2016-11-25 |  | 2016-12-02 | 2016-11-29 | QOE dependent hierarchy levels 1 to 3 are finished
80 |  |  |  | Task | Populate QOE on encode_histo_cols_agreg | HIgh | Adrian | Overdue | 2016-11-28 |  |  | 2016-12-02 |  |  | Problems on qoe_data and qoe_voix. Waiting for new data set
81 |  |  |  | Task | Validate if qoe_sms formula and output is the same with CEM calculation on daily aggregated tables | Medium | Adrian | Closed | 2016-12-01 | 2016-12-01 |  | 2016-12-05 | 2016-12-05 | Will use formula based on qoe_rules
82 |  |  |  | Task | Build correlation matrix on all usuable aggregated tables | Medium | Adrian | Completed | 2016-12-01 | 2016-12-01 |  | 2016-12-01 | 2016-12-01 | Provided summary. *init* and *Ok* show perfect linear relationship. Waiting for answers
83 |  |  |  | Task | Compare distinct HEXIMSIs among events and aggregated tables | Medium | Adrian | Completed | 2016-12-08 | 2016-12-08 |  | 2016-12-13 |  |  | 2G events only contain failed events. For 3G, voice only record failed events, SMS and Data contain successful events
84 |  |  |  | Clarification | What does the :1 operator mean in the denominator of the qoe_data | Medium | Etancesys | Completed | [5 empty] | When the L3 KPI contain at least one count, it puts one count to the denominator
85 |  |  |  | Clarification | The 2g and 3g events contain 400k+ distinct HEXIMSIs and GPRS events contain 200k+ events. Is this only a subset of the active subscribers? Because the subscribers contain 6M+ records | Medium | Etancesys | Completed | [5 empty] | Discussed in steerco 2
86 |  |  |  | Clarification | There are no terminating calls included in the aggregated table | Medium | Etancesys | Not Started | [5 empty] | Discussed in steerco 2
87 |  |  |  | Issue | Everytime there is a successful call (OcInit…), there is a corresponding failed call (OcKo…), which doesn’t make sense which scores the qoe_voix to 5 for any successful call and 0 for failed calls. Needs clarification on counters. | Medium | Etancesys | Not Started | [5 empty] | Discussed in steerco 2 | Will calculate formula from hourly to daily
85 |  |  |  | Issue | Some SMS related KPIs (i.e. SMSMTStatKo3g) are not treated as failed counters but the naming convention suggests that it is a failure. | Medium | Etancesys | Not Started | [5 empty] | Discussed in steerco 2 | Will calculate formula from hourly to daily
86 |  |  |  | Issue | SmsMoOkOffNetF3g as successful SMS’s, SmsMtOkOffNetF3g as successful SMS’s, SmsMtOkOffNetF2g as successful SMS’s, SmsMoKoFixeB2g as a 2g problem, which is all correct according to the formulae. Etancesys does not pick up those. | Medium | Etancesys | Not Started | [5 empty] | Discussed in steerco 2 | Will calculate formula from hourly to daily
87 |  |  |  | Task | Build steerco 2 deck | High | Adrian / Jovan | Completed | 2016-12-12 |  |  | 2016-12-16 | 2016-12-22
88 |  |  |  | Task | Rebaseline project timeline | Medium | Adrian | Completed | 2016-12-12 | 2016-12-12 |  | 2016-12-16 | 2016-12-22
89 |  |  |  | Task | Send missing KPIs to Jovan so that it can be included in the questions for the meeting | Medium | Adrian | Completed | 2016-12-15 | 2016-12-16 |  | 2016-12-15 | 2016-12-16 | In the QOE v2 Hierarchy, all of the highlighted KPIs in red are missing from encode_histo_cols_agreg.
90 |  |  |  | Task | Compile events from three tables (calls_details, calls_details_3g, calls_details_gprs) into one table for a sample for HEXIMSIs | Medium | Adrian | Completed | 2016-12-12 | 2016-12-12 |  | 2016-12-14 | 2016-12-15 | Also, it includes the compiled events from the three tables – 2G, 3G and GPRS so we can check if it contains failed events only. · For 2G and 3G voice where the duree_cnx AND duree_ringing AND duree_ringing > 0 = all failed events · For SMS, the events contain acknowledge receipt and delivered, so I assume it also includes successful ones · For GPRS, it includes events that have no rejcause · For 3G data PS, all have rej_cause; I am not sure what does Data PS and PS mean and how do they differ.
91 |  |  |  | Task | Compare the hourly count and aggregate it to daily by IMSI aggregation then compare if the numbers would match. | Medium | Adrian | Completed | 2016-12-12 | 2016-12-12 |  | 2016-12-14 | 2016-12-15 | None of the KPIs differ with the aggregation except the KPIs calculated by CEM which some are incorrect and most are due to distinct count and average-based KPIs
92 |  |  |  | Task | Compute for missing phone models based on distinct HEXIMSIs | Medium | Adrian | Completed | 2016-12-12 | 2016-12-15 |  | 2016-12-15 | 2016-12-15 | 17% of the 466k+ distinct HEXIMSIs from imsi_jour have no phone model attribute attached to it. This is based on the code_tac from last_mobile joined with ota_devices table.
93 |  |  |  | Task | Compute for missing distinct combined LAC CI based on ci_jour | Medium | Adrian | Completed | 2016-12-12 | 2016-12-15 |  | 2016-12-15 | 2016-12-15 | There are 77% missing distinct LAC CI of the 44,948 distinct concatenated LAC and CI from the ci_jour table; these are the LAC and Cis that at least generated one event based on the ci_jour table.
94 |  |  |  | Task | Compute for missing distinct combined LAC CI based on encode_histo_cols_agreg | Medium | Adrian | Completed | 2016-12-12 | 2016-12-15 |  | 2016-12-16 | 2016-12-16 | There are missing 76% (34,573 / 44,956) distinct LAC CI in the encode_histo_cols_agreg when joined with geo_reg_cells table. This is almost consistent with the 77% from the ci_jour table.
95 |  |  |  | Task | Compute for missing handset phone models based on distinct HEXIMSI | Medium | Adrian | Completed | 2016-12-12 | 2016-12-15 |  | 2016-12-15 | 2016-12-15 | All of the 466k distinct HEXIMSIs from imsi_jour have contract attribute.
96 |  |  |  | Request | Classify contract type, most are legecy | Medium | Etancesys | Not Started | 2016-12-16 | 2016-12-21
97 |  |  |  | Task | Aggregated from hourly to daily retaining LACCI and IMSI | Medium | Adrian / Rowen | Completed | 2017-01-06 | 2017-01-06 |  | 2017-01-11 | 2017-01-12
98 |  |  |  | Task | Collapse phone model variants (build hierarchy of phone models) | Medium | Adrian | Completed | 2017-01-12 | 2017-01-12 |  | 2017-01-23 | 2017-01-23 |  | Can collapse phone model variants with different TACs because they have the same qualities
99 |  |  |  | Task | Apply QOE SMS formula on SQL | Medium | Rowen | Completed | 2017-01-13 | 2017-01-13 |  | 2017-01-17 | 2017-01-17
100 |  |  |  | Task | Separate tables by product (voice, sms, data) because MySQL timesout with R connection | Medium | Rowen | In Progress | 2017-01-13 | 2017-01-13 |  | 2017-02-12 |  |  | Doing SMS because the formula for other products isnt fixed yet
101 |  |  |  | Task | Check subscriber table when it is updated | Medium | Adrian | Completed | 2017-01-12 | 2017-01-12 |  | 2017-01-13 | 2017-01-13 | After joining, there are 14,941,121 records. · There are 1,174,771 records where old code_tac = 0 (8%). There are 9,894,008 records where old code_tac is NA (66%). Which makes 11,068,779 blank old code_tac (74%). · Valid code_tac returns 3,872,342 records (26%). · Out of these records, 1,467,368 (38%) have different code_tac and 306,758 (8%) have no code_tac in the updated subscriber table.
102 |  |  |  | Task | Classify phone model - smart phone, feature phone, dongle, tablet, etc | Medium | Adrian | Completed | 2017-01-16 | 2017-01-18 |  | 2017-01-23 | 2017-02-02 | Done classifying top 80%
103 |  |  |  | Task | Prepare steerco 3 | Medium | Adrian / Jovan | Overdue | 2017-01-16 | 2017-01-19 |  | 2017-01-23
104 |  |  |  | Task | Apply model 1 and model 2 on SMS products on full dataset | High | Adrian | In Progress | 2017-01-16 |  |  | 2017-01-20 |  |  | In parallel with Task 107
105 |  |  |  | Task | Hourly aggregation from encode_histo_cols_agreg | Medium | Rowen | Completed | 2017-01-20 | 2017-01-20 |  | 2017-01-23
106 |  |  |  | Task | Rerun hourly and daily aggregation from encode_histo_cols_agreg | High | Rowen | In Progress | 2017-02-03 | 2017-02-03 |  | 2017-02-05
107 |  |  |  | Task | Run 60 models for all SMS KPI levels | High | Adrian | In Progress | 2017-02-03 | 2017-02-03 |  | 2017-02-08 |  |  | Script is ready, just waiting for Task 106
108 |  |  |  | Task | Draft logistic regression process to model SMS event table using calls_details3g | Medium | Adrian / Jeffrey | Not Started | 2017-02-08 |  |  | 2017-02-15

## Version Control
Version Number | Date | Changes
1 | 2012-10-01 | Created Check list
1.01 | 2013-10-01 | Added feedback from the meeting column and appended feedback
1.02 | 2018-10-01 | Added new tasks and created focus for next meeting
1.03 | 2021-10-01 | Added new tasks, removed number column
1.04 | 2024-10-01 | Modified tasks
1.05 | 2025-10-01 | Added resolution column
1.1 | 2026-10-01 | Added Task ID, Issue ID columns in Task tab. Added Issue tracker tab

## Project Timeline (hidden)
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Phase 1 | 1 | 6 | 1 |  | 30%
Business Understanding | 1 |  |  |  | 100%
Project plan
Data Understanding | 1 | 6 |  |  | 20%
Data Collection and Selection | 1 | 3 |  |  | 75%
Produce data collection report | 1 | 2 | 1 | 3 | 100%
Request for access to data | 1 | 1 | 1 |  | 90%
Identify data sources | 1 | 1 | 1 | 1 | 100%
Define table and column definitions | 1 | 3 | 2 |  | 50%
Data Transformation | 2 | 3 | 2 |  | 25%
Backup source data | 2 | 2 | 2 |  | 80%
Join technically correct data | 3 | 1 |  |  | 0%
Data exploration | 2 | 3 | 3 |  | 50%
Produce data exploration report | 3 | 5 | 3 |  | 90%
Compute for summary statistics | 3 | 1 | 4 | 1 | 100%
Look into sub-populations | 4 | 1 |  |  | 0%
Produce enhanced data definition report | 5 | 1 |  |  | 0%
Write the data quality report | 5 | 1 |  |  | 0%
Classification Map | 4 | 3 | 4 |  | 0%
Build hierarchy and weights | 4 | 2 | 4 |  | 5%
Visualize hierarchy | 6 | 2 |  |  | 0%
Create dataset | 6 | 1 |  |  | 0%
Phase 2
Data Cleansing | 7 | 3 |  |  | 0%
Apply appropriate cleansing techniques | 7 | 1 |  |  | 0%
Document cleansing rules | 7 | 2 |  |  | 0%
Produce final data dictionary | 7 | 2 |  |  | 0%
| 16 | 28 | 16 | 30 | 50%

## Project Plan
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 17 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan) | [13 empty] | % Complete (beyond plan)
[10 empty] | Phase 1 current state |  |  |  | Phase 2 current state |  |  | Christmas break |  |  |  |  | Present day | [9 empty] | Short work week (PH Holiday)
ACTIVITY | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10
| START | DURATION | START | DURATION | COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Phase 1 | 1 | 6 | 1 | 6 | 30%
Project Setup | 1 | 2 | 1 | 6 | 50%
Complete required access to data | 1 | 2 | 1 | 4 | 100%
Identify data sources | 2 | 1 | 2 | 5 | 100%
Initial assessment of infrastructure | 2 | 1 | 3 | 1 | 100%
Performance testing | 3 | 1 | 6 | 1 | 100%
Backup and lock tables | 3 | 1 | 6 | 1 | 100%
Data Dictionary and Validation Report | 2 | 4 | 2 | 15 | 80%
Validate data source with data dictionary | 2 | 3 | 3 | 14 | 50%
Understand table and column usage | 2 | 3 | 2 | 10 | 100%
Data exploration | 3 | 2 | 3 | 9 | 50%
Compute summary statistics | 3 | 1 | 3 | 3 | 50%
Look into sub populations | 4 | 1 | 3 | 4 | 50%
Understand data quality: Completeness analysis, uniqueness analysis, validity analysis, accuracy analysis, timeliness analysis | 4 | 3 | 5 | 8 | 50%
Produce enhanced data dictionary | 4 | 1 | 4 | 8 | 60%
Indicator Classification Map | 8 | 2 | 8 | 4 | 50%
Review hierarchy | 8 | 2 | 8 | 4 | 25%
Write validation report | 8 | 1 | 8 | 9 | 25%
Create dataset | 8 | 1 |  |  | 0%
Recommend visualization | 6 | 2 | 6 | 11 | 80%
Phase 2 | 7 | 14 | 7 | 10 | 10%
Invidividual Dimension Causality Models | 7 | 14 | 7 | 10 | 20%
Identify dimensions and products | 7 | 1 | 7 | 1 | 100%
Transform and clean data | 7 | 2 | 7 | 2 | 25%
Partition data sets | 8 | 1 | 13 | 2 | 25%
Train and validate preliminary models | 9 | 4 | 9 | 8 | 20%
Model building: qoe_voix with QKPIs | 13 | 2 | 9 | 4 | 0%
Model building: qoe_sms with QKPIs | 14 | 2 | 9 | 8 | 50%
Model building: qoe_data with QKPIs | 15 | 2 |  |  | 0%
Model building: qoe with QOE products | 17 | 1 |  |  | 0%
Optimize models | 13 | 5 |  |  | 0%
Validate model performance | 17 | 2 |  |  | 0%
Train and validate supplementary models | 17 | 5 |  |  | 0%
Model building: Aggregated KPIs with KPIs | 18 | 3 | 13 | 4 | 25%
Model building: Dimensions | 18 | 3 | 13 | 4 | 25%
Validate model performances | 20 | 1 |  |  | 0%
Run final models with complete data set | 21 | 2 |  |  | 0%
Produce model evaluation report | 21 | 2 |  |  | 0%
Visualization and Documentation | 23 | 3 |  |  | 0%
Design dimensionality matrices | 23 | 1 |  |  | 0%
Append model results with the classification map | 23 | 1 |  |  | 0%
Recommend visualization design | 24 | 1 |  |  | 0%
Write causality models documentation | 23 | 2 |  |  | 0%
Phase 3 | 25 | 3 |  |  | 0%
Recommendations | 25 | 3 |  |  | 0%
Develop recommendations | 25 | 1 |  |  | 0%
Training | 26 | 2 |  |  | 0%
Overall | 1 | 27 | 1 | 16 | 10%

## Proposed Project Plan
Project Planner
[5 empty] | Period Highlight: |  |  |  |  | 16 |  |  |  | Plan |  |  | Actual |  |  | Actual (beyond plan) | [13 empty] | % Complete (beyond plan)
ACTIVITY | PLAN | PLAN | ACTUAL | ACTUAL | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08
| START | DURATION | START | DURATION | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Phase 1 | 1 | 6
Project Setup | 1 | 6
Complete required access to data | 1 | 6
Identify data sources | 6 | 1
Initial assessment of infrastructue | 6 | 1
Data Dictionary and Validation Report | 16 | 3
Validate data source with data dictionary | 16 | 1
Understand table and column usage | 16 | 2
Data exploration | 16 | 2
Produce enhanced data dictionary | 16 | 1
Indicator Classification Map | 16 | 2
Build hierarchy and weights | 16 | 2
Write validation report | 16 | 1
Create dataset | 16 | 2
Recommend visualization | 11 | 1
Phase 2 | 7 | 22
Invidividual Dimension Causality Models | 7 | 22
Identify dimensions and products | 7 | 1
Transform and clean data | 7 | 2
Partition data sets | 8 | 1
Train and validate preliminary models | 17 | 4
Model building: qoe_voix with QKPIs | 17 | 2
Model building: qoe_sms with QKPIs | 18 | 2
Model building: qoe_data with QKPIs | 19 | 2
Model building: qoe with QOE products | 20 | 1
Optimize models | 17 | 4
Validate model performance | 20 | 2
Train and validate supplementary models | 21 | 5
Model building: Aggregated KPIs with KPIs | 21 | 2
Model building: Dimensions | 22 | 3
Validate model performances | 24 | 1
Run final models with complete data set | 23 | 2
Produce model evaluation report | 24 | 2
Visualization and Documentation | 26 | 3
Design dimensionality matrices | 26 | 1
Append model results with the classification map | 27 | 1
Recommend visualization design | 28 | 1
Write causality models documentation | 26 | 3
Phase 3 | 29 | 3
Recommendations | 29 | 3
Develop recommendations | 29 | 1
Training | 30 | 2
Overall | 1 | 31

## Legend
Priority | Status
High | Not Started
Medium | In Progress
Low | On Hold
Overdue
Completed
Cancelled